## Sheet1
Project Name: | Project Spyn - Gantt Chart |  | Week 1 |  | Week 2 |  | Week 3 |  | Week 4
| Tasks | Segments are divided on a daily |  |  |  |  | 2021-10-18 |  | 2021-10-22
Milestone 1 - Remote Control |  |  | 18/10/21 | 22/10/21 | 25/10/21 | 29/10/21 | Monday | Thursday | Monday | Thursday
Getting familiar with EV3 kit
Define the final design of the vehicle
Getting familiar with the motors
Connecting the EV3 Brick with Matlab
Execute code from the computer to the brick
Manipulate motors from the computer
Integrate inputs from the keyboard
Milestone 2 - Color Sensor Inclusion
Getting familiar with the color sensor
Integrate the sensor in the design of the car
Integrate the code to work with color sensor
Use inputs from the color sensor in navigation
Assembly of the car
Test Drive
Modify
Revision
Milestone 3 - Navigation
Getting familiar with the gyrosensor
Decide how we should utilize the gyrosensor
Code the gyrosensor
Attach it to our car
Test our code
Change our code based on tests
Revise until perfected
Work Completed
Work Remaining
Group 2:
Patrick Torpey
Ricardo Carrasco
Sohum berdia
Junichi koizumi