## Sheet1
Project Name: | Project Spyn - Gantt Chart |  | Week 1 |  | Week 2 |  | Week 3 |  | Week 4
| Tasks | Segments are divided on a weekly basis
Milestone 1 - Remote Control |  |  | 2021-10-18 | 2021-10-22 | 2021-10-25 | 2021-10-29 | 2021-11-01 | 2021-11-05 | 2021-11-08 | 2021-11-12 | 2021-11-15 | 2021-11-19
Getting familiar with EV3 kit
Define the final design of the vehicle
Getting familiar with the motors
Connecting the EV3 Brick with Matlab
Execute code from the computer to the brick
Manipulate motors from the computer
Integrate inputs from the keyboard
Milestone 2 - Color Sensor Inclusion
Getting familiar with the color sensor
Integrate the sensor in the design of the car
Integrate the code to work with color sensor
Use inputs from the color sensor in navigation
Assembly of the car
Test Drive
Modify
Revision
Milestone 3 - Navigation/Lift Mechanism
Getting familiar with the Moving Motor for the Lift
Decide how we should utilize the Moving Motor for the lift
Code the Motor
Assemble the lift
Test if it is carrying the person
Attach it to our car
Test our code
Change our code based on tests
Revise until perfected
Final Testing of the Lift Mechanism
Milestone 4 - Movemement through Maze and Recognition of Walls
Getting familiar with the UltraSonic Sensor
Decide how we should utilize the UltraSonic Sensor
Coding the UltraSonic Sensor
Testing out the sensor and its functions in the maze
Recoding and repairing the car/sensor
Checking out the Gyrosensor
Finding the use of the gyrosensor
Coding the GyroSensor
Getting Familiar with the Touch Sensor(s)
Attaching the Color Sensor to the vehicle
Coding the color sensor
Testing the co-ordination of the Color, Gyro and Ultrasonic Sensor
Testing the co-ordination of the sensors and the lift mechanism
Resolving any issues faced by the UltraSonic Sensor
Resolving any issues faced by the GyroSensor
Resolving any issues faced by the Color Sensors
Maze Testing
Work Completed
Work Remaining
Group 2:
Patrick Torpey
Ricardo Carrasco
Sohum berdia
Junichi koizumi